## LOE
Client: TiresUSA | Effot Name: Demonstration Site |  | Due Date: October 31, 2016
Major / High-level task
Documentation
| Reqs | 0 | Flushing out the requirements, We can use current system for most things. this includes reviewing wishlist
| SDD/Tech Specs | 0 | Includes updating req traceability matrix, use case, class, sequence and dynamically createderd diagrams, source control Strategy, deployment Strategy, delivery Strategy
| CMP | 2 | Configuration Management Plan
| SIP | 2 | Software Installation Plan
Environment Set up |  |  | Jenkins, SVN, web site/CF/DB creation
| Local | 3
| Test | 3
| Stage | 1
| Prod | 1
Development
| Set Up and Configuration | 8 | Includes Implementing deployment and delivery concessions from design tasks
| Framework, Dependency Injection Configuration | 5 | CommandBox with DocBox, TestBox
| Entity Object Creation/Displaying/Persisting | 11 | Create entity Objects to design spec
| Validation | 6 | Simple and complex validation and Display
| Localization | 0 | Assuming 2 languages and units of measure
| Search per Entity Tpe | 0 | Creating Search form with filters, the results page, and multiple and single detail page e.g. Animals
| Admin/Back Office | 10 | Assumes three types of resources, basic login and work flow and coded as stand alone which may not be the case
| Search | 10 | Includes search mechanism(Probably dynamic query), results display and Resource landing page
| Unit Test Creation | 5 | Basic unit tests that can can be kicked off via automation or manually
| Reporting | 0
| UI | 60 | Basic bootstrap responsive skin, platform independent and portable device capable
Application Testing
|  | 10 | Ensuring all demo steps can be completed successfully
Deployment/Delivery Testing
|  | 5 | Virtualization, spin up instance of IIS, lucee and db - Vagrant, Virtual Box Windows 2012
Mirgrations Scripts
| SQL Script to export/Import data from old db to new | 0
| GUI from site to automate data migration | 0
Sub Total |  | 142
Padding | 10% | 14.2
Total |  | 156.2
Assertions
This is not an exhustive LOE, but covers the high level tasks
Lucee - No more 6 digit license costs, if needed we can buy a support contract for development support
MySQL 5
Caveats

## Schedule
Epic | Sprint | Task | Start | End
Documentation, Configuration and Set Up | 1 | Proposal, LOE, Schedule | 2016-10-02 | 2016-10-03
|  | Create Source Control Repository | 2016-10-03 | 2016-10-03
|  | Application Archetecture Diagram | 2016-10-04 | 2016-10-04
|  | Usae Case Diagram | 2016-10-04 | 2016-10-04
|  | Class Diagram | 2016-10-04 | 2016-10-04
|  | Local VM Created | 2016-10-05 | 2016-10-05
|  | Initial Sysytem Archetecture deployed locally | 2016-10-05 | 2016-10-05
|  | Deployment AWS Process figured out | 2016-10-06 | 2016-10-06
Development, Registration/Login | 2 | Registration Form | 2016-10-12 | 2016-10-12
|  | Persist to DB | 2016-10-13 | 2016-10-14
|  | Profile landing page | 2016-10-14 | 2016-10-14
|  | Create test/Production AWS sites | 2016-10-15 | 2016-10-15
Importing Inventory Tire Data | 2 | Import form | 2016-10-14 | 2016-10-14
|  | Persist to data | 2016-10-14 | 2016-10-15
|  | Create make and Model Search Data | 2016-10-15 | 2016-10-15
|  | Create tire size search criteria - related select | 2016-10-15 | 2016-10-15
|  | Search Forms - make/model, tire size | 2016-10-15 | 2016-10-15
|  | Results Display | 2016-10-16 | 2016-10-16
|  | Detail Display | 2016-10-16 | 2016-10-16
GUI | 3 |  | 2016-10-17 | 2016-10-24
Demo Steps per Feedback | 3 | Login | 2016-10-17 | 2016-10-21
|  | Add tire Data | 2016-10-17 | 2016-10-21
|  | Search | 2016-10-17 | 2016-10-21
|  | Results | 2016-10-17 | 2016-10-21
|  | Details | 2016-10-17 | 2016-10-21
|  | Modify all domain Registrar Records Point to AWS | 2016-10-21 | 2016-10-21
GUI Integration / Feedback | 4 | Comiit Initial skin | 2016-10-21 | 2016-10-21
|  | Create single colum template | 2016-10-22 | 2016-10-22
|  | Create two colum template | 2016-10-22 | 2016-10-22
|  | Add pages | 2016-10-23 | 2016-10-23
|  | Changes Per Feedback | 2016-10-21 | 2016-10-27